TERMS OF REFERENCE for CLUSA-NRM FORESTRY FIELD COORDINATOR

YEAR STARTING NOVEMBER 2001

Work together with the Forest inventory and mapping advisor, CLUSA Area Training Coordinators and field facilitators, and the Forest Department to do the following:

1.  CHIULUKIRE JOINT FOREST MANAGEMENT PLAN

- Follow signing of the draft plan at the Chief’s and Forest Department levels

- Assist in implementing elements of the plan:

- Help develop training materials necessary for VRMAC operations

- Using management plan chapters, help develop the ecology-oriented sensitization materials for the user groups, especially broom makers, charcoal producers, hunters, and all those harvesting renewable resources from inside the forest

- Follow up on heretofore un-involved farmers, especially in the northwest corner of the forest

- Participate in developing the establishment of forest-based businesses with the Chiulukire team and FD

- Coordinate informational sessions and field trips for FD, other projects, VRMAC members, and District Councils as needed

2. PETAUKE FOREST MANAGEMENT ACTIVITY

- Help develop a modest 2-year forest management plan for the open areas chosen for intervention during 2001

- Identify further needs in material and personnel to accomplish the planned activities; this may involve a preliminary Village Resource Assessment

3. MPHOMWA HILLS FOREST MANAGEMENT PLAN PREPARATIONS

- Assist in compiling VRA reports from Oct-Nov 2001

- With the GFs and the Resource Informants, present the results of the VRA report back to the chiefs and the villagers

- Assist in planning, training, and execution of technical inventory in 2002

- Assist in workshops and planning exercises leading up to development of a management plan in 2002

4. OTHER DUTIES

- Submit quarterly reports to the CLUSA-NRM programme coordinator on work completed, problems encountered, and proposed solutions

- Coordinate with cartographer on mapping and data needs

- Coordinate with Provincial and District Forestry Offices on technical and project issues and fieldwork

- Advise and train in forestry fieldwork for GFs through CLUSA Area Training Coordinators in Mambwe, Petauke, and Katete areas

- Assure proper submission of perdiem pay sheets during each field mission

- Assist in development of annual workplan

- Liaise regularly with Forest Dept at Provincial and District levels